## Template
RISK ANALYSIS TABLE for {Condo Management System}
Last Update:
Ranking | Threats (1) | Vulnerabilities (2) | Contextual factors | Risks (3) | Likelihood from 1 to 5 | Impact from 1 to 5 | Reduction of Threats (Acceptance Strategy) | Reduction of Vulnerabilities (Protection Strategy) | Level of residual Risk
16 - High | Time Risk | - All the students working on the project are taking 4 or more classes and don't have unlimited time to work on the project, students will be busy with exams from other courses and other assignments to dedicate all their time to the project | We only have 12 weeks to complete the project and only 10 team members. | to be subjected to a time risk. | 3 | 4 | By efficient planning, we can make sure all the features we need are complete. | Removing the more unnecessary features and saving them for last. | 6 - Low
8 - Medium | Application Risk | We won't have infinite opportunities to show our product to the client and the product won't be ready until the later stages of the semester. | The client's requirements are unlikely to change before the deadline. | to be subjected to a application risk | 2 | 4 | Survey our solution to see if it theoretically makes sense. Proper testing before more costly implementations. | do it again next semester or replan the solution. | 4 - Low
9 - Medium | Skill Risk | Some team members may not be familiar with the proposed technologies; therefore, they should take the necessary steps to familiarize themselves with them. | Only two of our team members have good knowledge of the stack we plan on using, but they can easily teach the basics to the other members | to be subjected by a skill risk | 3 | 4 | Proper planning and use of our programmers' skills. | hire additional more skilled individuals to make up for the lack and teach. | 5 - Low
8 - Medium | Legal Risk | There are lots of laws and regulations related to condo management. | Depending on whether the condominium association is a cooperative, homeowners' association, or another type of legal organization, the legal requirements could change. | to be subjected by a legal risk | 1 | 5 | Reviewing legal conventions or precedent is beyond the scope of our project, but making a minor change | We will revert to the old state of the system if something serious arises | 4 - Low
8 - Medium | Fraud Risk | The project faces a fraud risk, where malicious actors may exploit it to gain unauthorized access and potentially steal user data. | The risk/reward for commiting fraud on that kind of project is way too bad for that to be realistic | to be subjected by a fraud risk | 1 | 5 | We believe that the likelihood that any of our team would do something like that is extremely low since there is almost no incentive to steal our clients' information, since it has little utility outside of the system and the legal repercussions would far outweigh the upside. | We will forward the pertinent information to law enforcement if we believe a crime was committed. | 4 - Low
10 - Medium | Scalability Risk | Insufficient infrastructure scalability poses a vulnerability, potentially hindering website performance under high user or operational loads. | Our application is not likely to have enough clients for it to be subject to scalability issues. | to be subjected by a scalability risk | 3 | 3 | Mitigate by using a scalable and reliable infrastructure and use load testing for the platform to ensure that its scalability is acceptable | Try alternate deployment methods and services and change the faulty algorithms if applicable | 6 - Low
2 - Very low | Team Dynamics Risk | Inadequate communication channels and a lack of team-building activities may result in strained relationships and misunderstandings among team members, potentially compromising collaboration, cohesion, and overall project effectiveness. | All of our team members are chill and don't look for conflict, so it's easy to avoid | to be subjected by a dynamic risk | 2 | 1 | Proper team meetings and encourage team communication. | Assess the teams composition and explore the possibility to invoke sub teams to avoid any more conflicts within team members. | 2 - Very low
10 - Medium | Security Risk | Overlooking privacy loopholes within our systems may lead to security issues, as these gaps could potentially be exploited by malicious entities, posing a threat to the overall security of our data and systems. | Only one of our team members has real cybersecurity experience so we probably can't make a state of the art security system but we can implement basic security measures | to be subjected by a security risk | 1 | 5 | Avoid by implementing security measures like 2FA, encryption and DDOS protection | Make a subteam that will be in charge of cybersecurity if it becomes a relevant problem | 5 - Low
15 - High | Risk Associated with Technology Compatibility | Team members who use MacBooks might have trouble using some of the technologies selected for the project | 3 of our team members use a macbook as their primary work computer | to be subjected to a Risk Associated with Technology Compatibility | 4 | 4 | depending on pair programming as a means of cooperation. Assist team members in learning how to use pair programming or adjust to new technologies by offering guidance and assistance | If required, look into other tools or development environments that work with MacBooks | 9 - Medium
12 - High | Availability of Resources Risk | An unexpected trip by a team member could affect the status of the project and connections within the team. | Since the tasks for this sprint are relatively independent, there is a chance that even if someone goes on a trip like that, it won't affect the project | to be subjected to an availability of resources risk | 4 | 2 | Assign tasks to the remaining team members and modify deadlines as necessary | Ask team members if they have anything like that planned so we can work around it | 9 - Medium
16 - High | Platform Change risk | Changing platforms from Uno to React might create problems | Changing platforms from Uno to React sets us back significantly in terms of frontend progress, since the knowledge that we learned from doing Sprint 1 with it will mostly go to waste. | to be subjected to a platform change risk | 5 | 4 | Use Chris as a resource for frontend developers since he has by far the most experience with the new framework. Chris is able to help the other developers with most of their bugs | Make a common document with the bugs and errors that the frontend team encounters and the solution so that others won't have to figure it out themselves, wasting even more time | 10 - Medium
15 - High | Code Coverage testing delay risk | The code coverage testing could take longer than expected due to external matters, which would affect the project overall schedule | Covering code in our project can vary from very simple to very complicated. Some of our functions have multiple nested conditions which make testing all paths fairly difficult | to be subjected to a code coverage testing delay risk | 3 | 5 | Provide more resources and continue the testing process into later sprints, if the code coverage testing can’t be done in Sprint 3. We will make sure that other important tasks are not missed | Code coverage testing is made as a top priority in the next sprint and assigns multiple developers from the team to complete testing. | 9 - Medium
15 - High | Security Risk | The condo management system could be exposed to security risks, such as virus attacks, hacking, and data breaches, which is dangerous to the data and system reliability | Designing a system that is invulnerable to outside attacks is almost impossible. | to be subjected to a security risk | 2 | 5 | Create backup plans, communicate more with the stakeholders, and create strategies for the security so we can react quickly to any harm | Reduce the risk by increasing the security measures, such as firewalls, robust security measures, regular evaluation of the security | 8 - Medium
15 - High | Compliance with Regulations Risk | laws or industry standards might change at any point in time, that will impact how the condo management system will operate or what it will be able to do | A system that is used to manage real estate properties is likely to be subject to a certain amount of regulation | to be subjected to a compliance with regulations risk | 2 | 5 | The risk of non-compliance can be reduced by outsourcing changes or updates to guarantee that the system complies with industry standards and laws | Make a contract with third-party providers to keep up with the updates and changes, and they can inform the team on what to do and how to react to these changes | 8 - Medium
12 - High | Management Risk | The likelihood of internal mismanagement that might result in project failures or errors. This may involve poor decisions, insufficient allocation of the resources, poor communication, and failure to adapt to new changing conditions. | The team's communication, leadership, and organizational structure. The team's agility and previous experience working on related projects are important. | to be subjected to a management risk | 3 | 3 | Develop strong management procedures and plan more ways to communicate in order to reduce management risk. This needs solid planning, continuous reviewing, and having backup plans. | Develop a good risk strategy that will show detailed steps that needs to be done when mismanagement occurs. To better solve identified issues, the plan should outline how resources should be reallocated, adjust the scopes of the project or change the management methods. | 6 - Low
9 - Medium | Technical Development Risk | The chance that the condo management system's technology will age and become less effective, and may become unsuitable with the new hardware and software, that leads to a poorer user experience than the new systems. | The rate of the technological change and the condo management system's focus to the continuous improvement in research and development. | to be subjected to a technical development risk | 4 | 5 | Stay up to date with the customer and users needs and keep up with the technological developments. That will make it easier to upgrade system components and schedule regular updates. | Develop a strategy to make continuous reviews on technology and identify the components that may become outdated. | 12 - High

## Example
RISK ANALYSIS TABLE for BASE
Last Update:
Ranking | Threats (1) | Vulnerabilities (2) | Contextual factors | Risks (3) | Likelihood from 1 to 5 | Impact from 1 to 5 | Reduction of Threats (Acceptance Strategy) | Reduction of Vulnerabilities (Protection Strategy) | Level of residual Risk
9 - Medium | Transport accidents (Indirect threat) | Fleet: - Large fleet (vehicle and motorbikes) - Bad state : 50% of cars are in bad state - 30% of motorbike are in bad state - high number of daily movements with a lack of coordination RH - Lack of leadership of direct line managers of drivers - No regular team meetings and refreshing trainings - no respect of drivers' and passengers' regulations Communication - No follow up of movements of vehicles and motorbikes - No strategy of communication equipment (movements) - no global covering (phone and radio) | State of roads enhance speed on highways with unappropriate equipment, uneven on secondary roads, animals Driving (in general) - Bad state of national fleet, especially public transports. - Poor respect of raods regulation - wet season and dark hours are more risky | To be subjected to a transport accident | 3 | 3 |  | • System of regular control (respect of rules and regulation) to be implemented • Review and update of SOP • Implement communication strategy, rules and system between vehicles and bases • Plan of renewing vehicles • Improve the planning of movement (reduce number of movement and reduce speed) • Maximal driving distances, obligation for drivers to take a break • Plan coaching of direct line managers and trainings session for drivers and bikers •Plan regular team meetings/workshop •Officialize adherence to rules by drivers and passengers (Review of vehicle policy, sensitization, trainings and signing by every one) • implement a strict adherence to use of safety clothing and equipments • plan regular Safety refreshing trainings (drivers and programs) | 6 - Low
8 - Medium | EID / RCIED / Anti tank mines (Indirect threat) | . Movement to our intervention area . Mistaken identity | Report major incidents: . Suspected IED discovered on XXX main road on 11th November . Few incident have been occurred on the road between XX . One RCED attack against demining organization on 2010 . One RCED on the road from XXX . 2 RCED attack in XXX in 2009. on 2010 one more on the road from XXX | To be subjected to an EID/RCIED/Anti tak mine explosion | 2 | 4 | . Community support & contact with AOG | . Limitation of movement . Collection of information from locals before using the road (constant re-assessment of the situation) . Not to be the 1st car to take the road . Use of alternative roads . Use of low profile cars . Movement with public transportation | 5 - Low
8 - Medium | Suicide attack (Indirect threat) | . Wrong time in wrong place related to: . convoys . Governmental, UN, embassies buildings | . The most recent suicide attacks was in xx, the target was XXX convoy district in XX area . Attack on XXX in district XXX in July. . In 2009: complex attacks to XXX . Most of suicide attacks are occurring in the morning before 9AM. | To be subjected to a suicide attack | 2 | 4 |  | . Avoid going to Governmental offices before 9am. Official meetings after 9:30am . UN guest houses, GH and offices located close to GOA and UN buildings and embassies are no go areas. . Restricted list of recreative locations. . Distance from military convoys . Avoid traffic congestions. . Low profile policy Refer to the current SOPs | 4 - Low
8 - Medium | Kidnapping (Crime related) | . Presence of 8 International staff in KBL . Movements during and out of working hours | . Strong presence of Afghan security personnel in the city . No kidnapping of NGO international staff reported in 2009/2010 . 2008: NGO staff kidnapped in district 5 CH Qambar + kidnapping AFRAN in Karte Parwan. | To have an international staff victim of a kidnapping or an hostage taking | 2 | 4 | low profile policy | . Confidentiality & unpredictability of movement, . No use of HF and VHF . Group movement & presence of a guard in addition of a driver for any movement . Walking restriction. . Mapping: no go areas clearly identified. . Low profile policy Refer to the current SOPs | 4 - Low
6 - Low | Crowd/mob/riot (Indirect threat) | . Wrong time, wrong place during movements. . Population perception of NGO | . In 2010, violent demonstration in district X and 5 between XX and XX. . Demonstration of election candidate followers due to result of election. . 2010: media reports that NGOs are involved in convertion to chrystianity. . NGO perception fluctuant | To be subjected to a crowd / mob/riot | 2 | 3 | . Low profile policy . To respect the culture of the people in terms of religion and living. | . Good information collection and adapted movement plan . Communication with teams during movement: alert system . Only HoM in contact with media . No sign and logo to the office and GH Refer to the current SOPs | 3 - Very low
2 - Very low | Armed Robbery (Crime related) | . Perception of expatriates & international organizations . Cash movement | . Criminality is assessed as being low for the time being | To be victim of a robbery | 2 | 1 | . low profile policy . good relations with neighbours in case of evacuation from ACF premises | . 2 guards per shift, . Existing & implemented cash policy Refer to the current SOPs and national security plan | 2 - Very low
CONFIDENTIAL